## Software Test Cases (STC)
Field | Value
Jira Ticket | SA4E-337
Title | Document Indexer: Fix auto-ingest into KB Memory with correct type/tags
Author | QA Agent
Version | 1.0
Date | 2026-10-05
Status | Draft — pending BA review (Review Gate)
Related STP | STP-v1.0-SA4E-337.docx
Related FSD | FSD.md (v1.0)
Related BRD | BRD-v1.0-SA4E-337.docx

## SDLC-Agents-4-Enterprise — SA4
Version | Date | Author | Changes
1.0 | 2026-10-05 | QA Agent | Initiate document — derived from BRD §2.3 stories/ACs, FSD §3 (UC-01..06, BR-01..28), FSD §10 (TC-01..30), TDD §11 (E2E design), and executed evidence

## Document Information
Category | ID Range | Count | Priority | Execution Status
PBT — Property-Based | — | 0 (N/A) | — | Level not applicable (STP §2.1)
UT — Unit (automated) | UT-01 to UT-82 | 82 | High | 82 PASS (UT-79..82 executed 2026-10-05)
IT — Integration (automated) | IT-01 to IT-09 | 9 | High | 9 PASS
E2E-API — REST E2E (automated) | E2E-API-01 to E2E-API-14 | 14 | High | 14 PASS
E2E-UI — Browser (automated) | — | 0 (N/A) | — | Level not applicable (TDD §11.5)
SIT — Manual (VS Code UI) | SIT-01 to SIT-04 | 4 | High | 0 executed (NOT_RUN — Phase 6)
Total |  | 109 |  | 105 PASS, 0 PLANNED, 4 SIT pending

## Revision History
ID | Title (test name) | Priority | Requirement | Preconditions / Test Data | Expected Result | Status
UT-01 | registers routes without error | High | UC-01..06, BR-03 | Fresh Hono app + registry mock | registerIndexRoutes completes; no throw | PASS
UT-02 | indexError returns enriched shape for PROJECT_REQUIRED | High | FSD §9, TDD §12 | indexError('PROJECT_REQUIRED') | Enriched {error, details, action} shape | PASS
UT-03 | indexError enriches ENOSPC | Medium | FSD §9 | indexError('ENOSPC') | Enriched message + Retry action | PASS
UT-04 | indexError enriches EACCES | High | FSD §7.3, TDD §7.3 | indexError('EACCES') | Enriched message (unsafe path) | PASS
UT-05 | indexError caps details to 2000 chars | Medium | TDD §12 | Details string > 2000 chars | details.length ≤ 2000 | PASS
UT-06 | indexError default maps to Retry action | Low | TDD §12 | Unknown error code | Falls back to Retry action | PASS
UT-07 | 401 when Authorization header missing | High | FSD §7.1, TDD §7.1 | Request without Authorization to /api/index/documents | HTTP 401, enriched body | PASS
UT-08 | 401 when Bearer token invalid/expired (validateSession null) | High | FSD §7.1 | validateSession → null | HTTP 401 | PASS
UT-09 | 400 when files array missing on /api/index/documents | High | TDD §3.1 | POST body {} | HTTP 400 + details | PASS
UT-10 | 400 when files array missing on /api/index/source | High | TDD §3.3 | POST body {} | HTTP 400 + details | PASS
UT-11 | 400 with details on sync-pega when projectId missing | Medium | FSD §7 | sync-pega without projectId | HTTP 400 + details | PASS
UT-12 | 503 with details on sync-pega when memory module not ready | Medium | TDD §12 | registry module status ≠ ready | HTTP 503 + details | PASS
UT-13 | rejectedReasons per-file: ../evil.ts + absolute path rejected with EACCES | High | FSD §7.3, TDD §3.1 | files: ../../evil.ts, absolute path | rejected + rejectedReasons[].code='EACCES'; no write outside temp | PASS
UT-14 | writeFilesPhase escape via normalize (a/../../evil.ts) still blocked | High | FSD §7.3 | Path escapes after path.normalize | Still rejected EACCES | PASS
UT-15 | 429 when exceeding INDEX_CONCURRENCY_LIMIT (4 parallel /api/index/source) | Medium | TDD §3.3 | 4 concurrent requests | HTTP 429 + retryAfter: 2 | PASS
UT-16 | sanitizePathSegment strips unsafe chars and falls back | High | FSD §7.3 | .., a/b, null bytes | Safe segment, no traversal | PASS
UT-17 | resolveIndexTempBase uses cross-platform base (not hardcoded Windows) | Medium | TDD §3.1 | Windows + POSIX-style ids | Portable temp base path | PASS
UT-18 | resolveSafeTargetPath blocks traversal, absolute, backslash, encoded, drive | High | FSD §7.3 | ..\\, /etc/x, C:\, %2e%2e | All rejected | PASS
UT-19 | 403 enriched on /api/index/documents when KB_WRITE missing | High | FSD §7.1, TDD §7.2 | permissions without KB_WRITE | HTTP 403 enriched (BOLA) | PASS
UT-20 | 403 enriched on /api/index/source when KB_WRITE missing | High | FSD §7.1 | permissions without KB_WRITE | HTTP 403 | PASS
UT-21 | 403 enriched on /api/index/ingest-docs when KB_WRITE missing | High | FSD §7.1 | permissions without KB_WRITE | HTTP 403 | PASS
UT-22 | 403 enriched on /api/index/sync-pega-rules when GRAPH_MAINTAIN missing | Medium | FSD §7.1 | permissions without GRAPH_MAINTAIN | HTTP 403 | PASS
UT-23 | 202 on /api/index/sync-pega-rules when GRAPH_MAINTAIN granted | Medium | FSD §7.1 | GRAPH_MAINTAIN granted | HTTP 202 | PASS
UT-24 | 403 enriched when X-Project-Id outside JWT grant | High | TDD §7.2 (fail-closed) | X-Project-Id: other-project, grant excludes it | HTTP 403 | PASS
UT-25 | 200 on /api/index/documents when X-Project-Id inside JWT grant | High | TDD §7.2 | Project inside grant | HTTP 200 | PASS
UT-26 | QA-001/QA-002 happy path: 200 {ingested, errors, total} when handler ingests all staged files | High | QA-001, QA-002, UC-03, BR-15 | Staged temp files + handler mock (map without getDispatcher) returns ok | HTTP 200; counts correct | PASS
UT-27 | passes SA4E-337 args (type, tags, scope, content_base64) + tenant scope to the handler | High | UC-01, UC-02, TDD §6.2 | Same harness; capture handler args | args include type/tags/content_base64; _projectContext present | PASS
UT-28 | counts failed ingest (isError result) into errors/failedFiles | High | QA-001, BR-13, TDD §12 | Handler returns isError: true | Counted in errors + failedFiles[{file,reason}], not ingested | PASS
UT-29 | handler throwing is captured per-file (no 500) and reported in failedFiles | High | QA-001, TDD §12 | Handler throws per file | Per-file capture, HTTP 200 with errors, never 500 | PASS
UT-30 | 503 enriched when mem_ingest_file tool handler is unavailable | High | QA-001, TDD §6.2 | getToolHandlers() returns map without mem_ingest_file | HTTP 503, details='mem_ingest_file tool handler is unavailable'; no TypeError | PASS
UT-31 | returns {ingested:0, message} when temp folder missing | Medium | FSD EF-3, TDD §12 | No temp dir | {ingested:0, message:'No documents in Temp folder'} | PASS
UT-32 | inferTypeFromPath maps BRD/FSD/TDD/STP patterns | High | Bug #1, UC-01, BR-01..05 | docs/SA4E-1/BRD.md, FSD-embedded.md, TDD.md, STP.md, RUN-LOG.md, diagram.drawio, notes.txt | REQUIREMENT / REQUIREMENT / ARCHITECTURE / PROCEDURE / PROCEDURE / CONTEXT / CONTEXT | PASS
UT-33 | extractTagsFromPath extracts SA4E / feature tags from segments | High | Bug #2, UC-02, BR-06..11 | documents/SA4E-337/BRD.md, C:\ws\F3\TDD.md, docs/plain.md | ['sa4e','sa4e-337'] / ['feature','f3'] / [] | PASS
UT-34 | summarizeIngestResult classifies ok / Error / isError / unconvertible | High | QA-001, UC-03, BR-12..14 | Fixtures: {"status":"ingested"}, {"status":"unconvertible","reason":"no-tool"}, "Error: …", isError:true, null | ok/failed classification, reasons extracted, null → ok=false | PASS

## Test Case Summary
ID | Original ID | Title (test name) | Priority | Requirement | Preconditions / Test Data | Expected Result | Status
UT-35 | UT-010 | excludes files in diagrams/ folder | High | Bug #4, UC-04, BR-17, TC-22 | TEST-1/diagrams/arch.drawio + TEST-1/BRD.md | arch.drawio NOT discovered; BRD.md discovered | PASS
UT-36 | UT-011 | excludes files in testdata/ folder | High | UC-04, BR-17, TC-22 | TEST-1/testdata/data.csv + TEST-1/notes.csv | testdata path excluded; root notes.csv included | PASS
UT-37 | UT-012 | includes files in nested subdirectories | Medium | FSD §6.1 workflow, TC-30 | TEST-1/attachments/spec.pdf | Discovered | PASS
UT-38 | UT-013 | only includes files with indexable extensions | High | BR-05, TC-05 (extension gate) | report.docx, notes.md, script.exe, run.sh | .docx/.md included; .exe/.sh excluded | PASS
UT-39 | UT-014 | classifies known document names correctly | High | Bug #1, Story 1 AC-1..AC-4, TC-01..TC-04 | BRD.md, FSD.docx, TDD.pdf, STP.xlsx | REQUIREMENT / REQUIREMENT / ARCHITECTURE / PROCEDURE | PASS
UT-40 | UT-015 | unknown file names map to CONTEXT type | High | Bug #1, BR-02, Story 1 AC-5, TC-05 | meeting-notes.docx, api-spec.yaml | Both → CONTEXT | PASS
UT-41 | UT-016 | extracts ticket key from folder name | High | Bug #2, BR-07, TC-08 | documents/KSA-239/BRD.md | ticket = 'KSA-239' | PASS
UT-42 | UT-017 | classifies files with extra suffixes correctly | Medium | Bug #1, Story 1 AC-6..AC-7, TC-06, TC-07 | TDD-v1-KSA-26.docx, BRD_STORY_8.md | ARCHITECTURE (prefix) / REQUIREMENT (underscore) | PASS
UT-43 | IT-009 | mixed structure with exclusions | High | UC-04, BR-17 | BRD.md, FSD.docx + diagrams/, testdata/ dirs | Exactly 2 discovered | PASS
UT-44 | IT-010 | recursive subdirectory discovery | Medium | FSD §6.1, TC-12 (nested paths) | attachments/design.pdf, specs/api.yaml | Exactly 2 discovered | PASS
UT-45 | IT-012 | multiple ticket folders | Medium | BR-07 | KSA-1, KSA-2, KSA-3 each with BRD.md | 3 results; tickets [KSA-1, KSA-2, KSA-3] | PASS
UT-46 | (unlabeled) | ignores denylisted folders (templates) | High | BR-17, TC-22 | documents/templates/BRD.md | 0 results | PASS
UT-47 | (unlabeled) | indexes feature-named folders that are not ticket keys (GRAPH-EMAIL) | Medium | BRD Story 2 AC-3, TC-10 | documents/GRAPH-EMAIL/{BRD,FSD,TDD} | 3 results, ticket='GRAPH-EMAIL', BRD→REQUIREMENT | PASS
UT-48 | (unlabeled) | indexes files placed directly under documents/ root | Medium | BRD Story 2 AC-4, TC-11 | documents/overview.md | documents/overview.md discovered | PASS

## 1. Unit Test Cases — Backend R
ID | Title (test name) | Priority | Requirement | Preconditions / Test Data | Expected Result | Status
UT-49 | returns context when previous entry has structured_map with summary | Medium | Regression — TaskWorker.ts (Bug #5 file) | Prev entry with summary in structured_map | Context returned | PASS
UT-50 | returns null for first section (no previous entry) | Medium | Regression | No previous entry |  | PASS
UT-51 | returns null when source is null (single ingest) | Low | Regression | source = null |  | PASS
UT-52 | returns null when previous entry has empty structured_map | Low | Regression | structured_map = {} |  | PASS
UT-53 | returns null when previous entry has no summary | Low | Regression | No summary field |  | PASS
UT-54 | returns null on DB error | Medium | Regression | DB error injected | null, no throw | PASS
UT-55 | marks task failed immediately for invalid_payload error | Medium | FSD §9 reliability, TDD §5.4 | invalid_payload | Task failed, no retry | PASS
UT-56 | marks task failed immediately for symbol_not_found error | Medium | TDD §5.4 | symbol_not_found | Task failed | PASS
UT-57 | marks task failed immediately for invalid_json error | Medium | TDD §12 (bad enrichment payload) | invalid_json | Task failed (markFailed('invalid_json_payload')) | PASS
UT-58 | marks task failed immediately for entry_not_found error | Medium | TDD §5.4 | entry_not_found | Task failed | PASS
UT-59 | resets for retry on transient error with retries remaining | Medium | Reliability | Transient error, retries left | resetForRetry | PASS
UT-60 | marks failed when max retries exhausted for transient error | Medium | Reliability | Retries exhausted | Task failed | PASS
UT-61 | does NOT resetForRetry for any non-retryable data errors | Medium | TDD §5.4 | Non-retryable data errors | Stays failed | PASS
UT-62 | DOES resetForRetry for transient LLM errors when retries remaining | Medium | Bug #5 (LLM availability), FSD §9 | Transient LLM error | Retries → later fallback path reachable | PASS

## 2. Unit Test Cases — Extension
ID | Title (test name) | Priority | Requirement | Expected Result | Status
UT-63 | getIndexerOutput returns singleton channel | Medium | Bug #3/#6 regression — IndexerHttpClient.ts modified | Singleton Output channel instance | PASS
UT-64 | syncCodeSymbols returns string¦null | Low | Regression | Returns string or null | PASS
UT-65 | httpPostWithDetail maps 401 to Unauthorized but keeps details/action | High | Bug #3, FSD §9 (API error) | 401 → Unauthorized, details/action preserved | PASS
UT-66 | httpPostWithDetail ok-path keeps details/action undefined | Medium | Bug #3 | Success → no error fields | PASS
UT-67 | sendBatchWithRetry propagates details/action without retry (maxRetries=0) | Medium | Bug #3 | Error propagated, no retry | PASS
UT-68 | sendBatchWithRetry early-returns 401 with details/action intact (no retry) | High | FSD §9 | 401 short-circuit | PASS
UT-69 | sendBatchWithRetry propagates details/action when retries are exhausted | Medium | Bug #3 | Final error carries details | PASS
UT-70 | sendBatchWithRetry ok-path keeps details/action undefined | Medium | Bug #3 | Success path clean | PASS
UT-71 | formatIndexError prefers error.message and appends file | Medium | Bug #3 (BR-13 reasons), FSD §9 | Error message + file name in output | PASS
UT-72 | logTerminalIndexState complete logs success without phantom error detail | Medium | Story 3 AC, BR-15 | Success log only | PASS
UT-73 | logTerminalIndexState failed surfaces error.message and stack | Medium | Story 3 AC-4, FSD §9 | Failure log includes message/stack | PASS
UT-74 | pollIndexProgress exits promptly on phase=complete | Medium | Bug #3 (verification loop) | Polling exits when complete | PASS
UT-75 | pollIndexProgress timeout reports no phantom unknown-error detail | Medium | FSD EF-4 (timeout) | Timeout → explicit message, no phantom error | PASS
UT-76 | httpPostJson propagates fresh token via onTokenRefreshed + getCurrentToken | Medium | Regression — auth during long ingest | Fresh token propagated | PASS
UT-77 | httpGet propagates fresh token via onTokenRefreshed | Medium | Regression | Fresh token propagated | PASS
UT-78 | getCurrentToken undefined before any refresh | Low | Regression | undefined initially | PASS

## 3. Unit Test Cases — TaskWorke
ID | Title | Priority | Requirement | Preconditions / Test Data | Expected Result | Status
UT-79 | fallbackTagExtraction applies parent-path + content tags when tagAnalyzer absent | High | Bug #5, UC-05, BR-20, BR-21, BR-24, TC-14 | TaskWorker constructed without tagAnalyzer; payload source='…/SA4E-337/BRD.md', content with #### STORY; CSV rows dev/notes.md, docs-old/report.md, projects/x/y/file.md, root.md, empty source | processTagEnrichment → tags include sa4e, sa4e-337, brd, user-story; task COMPLETED; log Fallback tag extraction applied; root → documents; empty source → unknown | PASS (2026-10-05, local SQLite/vitest — backend/src/modules/memory/task-queue/__tests__/TaskWorker.fallback-tag.test.ts)
UT-80 | fallback tag deduplication + denylist skip | Medium | Bug #5, BR-22, BR-23, TC-15, TC-16 | payload existing_tags='sa4e-337', path segment SA4E-337 (duplicate); parent folder diagrams (denylisted); CSV rows backup/backup.md, archive/archive/doc.md, cache/cache/file.md | No duplicate tags; denylisted folder not used as tag; archive/archive/doc.md → [archive] (immediate parent only) | PASS (2026-10-05, local SQLite/vitest — backend/src/modules/memory/task-queue/__tests__/TaskWorker.fallback-tag.test.ts)
UT-81 | triggerDocumentIngest handles invalid JSON / non-OK status per BR-12 | High | Bug #3, UC-03, BR-12, TC-19, TC-20 | Mocked fetch: (a) 200 + invalid JSON; (b) 500 status | (a) returns zeros + warning ⚠️ Could not parse ingest response; (b) zeros + ⚠️ Document ingest failed: status 500; run continues | PASS (2026-10-05, local vitest (extension) — extension/src/services/__tests__/IndexerHttpClient.ingest.test.ts)
UT-82 | extractFallbackTags (TaskWorker.ts): nested folder secondary tag + root-level fallback | High | Bug #2/#5, BRD Story 2 AC-1/AC-4, Story 5 AC-2/AC-3, TC-11, TC-12, TC-13 | Paths: SA4E-337/attachments/spec.pdf, overview.md (root), attachments/spec.pdf | extractFallbackTags → ['sa4e-337','attachments'] (secondary present); root → documents fallback; non-ticket → immediate-parent tag (BR-20); never empty | PASS (2026-10-05, local SQLite/vitest — backend/src/modules/memory/task-queue/__tests__/TaskWorker.fallback-tag.test.ts)

## 4. Unit Test Cases — IndexerHt
ID | Title (test name) | Priority | Requirement | Preconditions / Test Data | Expected Result | Status
IT-01 | Full CRUD lifecycle: creates entry, processes task, updates structured_map | High | UC-03 verification loop, Bug #5 file regression | New entry + TAG_ENRICHMENT task | Entry created → task processed → structured_map updated | PASS
IT-01b | priority queue ordering: claimNext/claimBatch highest priority first | Medium | Reliability (queue) | Tasks with mixed priorities | Order: priority DESC, created_at ASC | PASS
IT-02 | Context chain between sections: section 1 summary → section 2 context | Medium | TaskWorker regression | Two sections, summary present | Context passed | PASS
IT-03a | Backward compatibility: old entry with structured_map="{}" | Medium | Regression | structured_map="{}" | Processes without error | PASS
IT-03b | Backward compatibility: old entry with minimal structured_map | Low | Regression | Minimal map | Processes without error | PASS
IT-04 | LLM timeout fallback: uses fallback extraction, still updates structured_map | High | Bug #5 adjacent (LLM unavailable), FSD §9, TDD §12 | llm.complete rejects LLM timeout; content 'Error: bug fix for login decision' | tags non-empty; extraction_meta.fallback_used=true | PASS
IT-05 | Context chain disabled: no context when config off | Low | Regression | enableContextChain:false | No context applied | PASS
IT-06 | Previous section fallback: null context when no summary | Low | Regression | Prev entry without summary | null context | PASS
IT-07 | structured_map fail → tags still update | Medium | Reliability (BR-11 tags survive) | structured_map update fails | Tags still updated | PASS

## 5. Unit Test Cases — Coverage
ID | Evidence ID | Title | Priority | Requirement | Steps (condensed) | Expected / Actual | Status
E2E-API-01 | E2E-01 | Server health + memory module ready | High | Entry criterion STP §2.5 | GET /health | 200; modules.memory=ready (actual: 200, memory=ready) | PASS
E2E-API-02 | E2E-02 | Create session → Bearer token with KB_WRITE | High | FSD §7.1, E2E auth setup | POST session create | Token 64 chars; KB_WRITE=true; perms=15 | PASS
E2E-API-03 | E2E-03 | Negative: no Authorization header → 401 | High | FSD §7.1, TDD §7.1 | POST /api/index/documents without header | HTTP 401 | PASS
E2E-API-04 | E2E-04 | Negative: missing X-Project-Id → 400 PROJECT_REQUIRED | High | TDD §7.2 fail-closed | POST without X-Project-Id | HTTP 400 | PASS
E2E-API-05 | E2E-05 | Stage 8 .md + 1 .drawio in resolveIndexTempBase() batch-docs | High | Bug #4 preconditions, UC-04 | Write staged files: BRD.md, DPG.md, FSD.md, RLN.md, STC.md, STP.md, TDD.md, UG.md, test-coverage.drawio | 9 files staged | PASS
E2E-API-06 | E2E-06 | POST /api/index/ingest-docs → 200 (QA-001 regression: was HTTP 500) | High | QA-001, UC-03 | POST ingest with Bearer + X-Project-Id | HTTP 200 {"ingested":9,"errors":0,"total":9,"failedFiles":[]} | PASS
E2E-API-07 | E2E-07 | Response JSON {ingested, errors, total, failedFiles} (Bug #3) | High | Bug #3, BR-15, TC-17 | Parse ingest response | ingested=9, errors=0, total=9, failedFiles=[] | PASS
E2E-API-08 | E2E-08 | All 9 staged files created a KB row | High | UC-03 verification, Story 3 AC | Query knowledge_entries (test DB) | 9 rows | PASS
E2E-API-09 | E2E-09 | Bug #1: type derived per doc — 8/8 correct, CONTEXT=0 | High | Bug #1, UC-01, BR-01..04, TC-01..TC-04 | Read type of 8 .md rows | BRD=REQUIREMENT, DPG=PROCEDURE, FSD=REQUIREMENT, RLN=PROCEDURE, STC=PROCEDURE, STP=PROCEDURE, TDD=ARCHITECTURE, UG=PROCEDURE; CONTEXT=0 | PASS
E2E-API-10 | E2E-10 | Bug #4: .drawio ingested (type=CONTEXT per TDD §3.2) | High | Bug #4, UC-04, BR-19, TC-21 | Read .drawio row | 1 row, type=CONTEXT (id=8); isIngestableFile() accepts .drawio | PASS
E2E-API-11 | E2E-12 | Tenant scope: project_id NOT NULL = SA4E-337, scope=PROJECT | High | FSD §7, TDD §7.2 | Read project_id/scope on all rows | All 9 rows project_id=SA4E-337, scope=PROJECT | PASS
E2E-API-12 | E2E-13 | Bug #2/#5: tags present after async TAG_ENRICHMENT (8 .md docs) | High | Bug #2, Bug #5, UC-02, BR-11, TC-08, TC-28 | Poll enrichment tasks until done; read tags | mdTagged=8/8, tasks COMPLETED=9 (e.g. BRD.md=knowledge-base,implementation,requirements,document-type; test-coverage.drawio=[]) — .drawio tags empty = known deviation (BRD Story 2 AC-2 vs denylist) | PASS (deviation noted)
E2E-API-13 | E2E-14 | Cleanup staging files, KEEP KB entries for SM inspection | Medium | Test data hygiene (STP §4.3) | Delete temp dir; recount KB | tempDeleted=true, kbRowsKept=9 (DB kept at isolated dir) | PASS
E2E-API-14 | E2E-15 | Negative: corrupted Bearer token → 401 | High | FSD §7.1 | POST with corrupted token | HTTP 401 | PASS

## 6. Integration Test Cases — Ta
Level | Count | Justification
PBT | 0 | Deterministic mapping functions covered by exhaustive input tables in UT (STP §2.1) — no random-input property worth automating for this bug-fix
E2E-UI | 0 | Bug #6 UI lives in the VS Code extension host (Output channel + toast), not a browser; Playwright in this repo targets admin web only (TDD §11.1/§11.5). Manual SIT-01..SIT-04 covers it

## 7. E2E-API Test Cases — Real S
Field | Value
ID | SIT-01
Priority | High
Type | Manual — Usability/Functional
Requirement | Story 6 AC-1..AC-3, Story 3 AC-1, UC-06, BR-27, BR-28, FSD TC-23
Preconditions | VS Code/Kiro with extension installed; backend running & reachable; workspace has documents/ with ≥ 5 files

## 8. Test Levels — Not Applicabl
Step | Action | Expected Result
1 | Run command palette → index command (Index Workspace → documents) | Indexing starts; Output channel "SDLC Indexing" auto-shown
2 | Wait for completion | Output shows summary title matching the selected operations ("Document Indexing Summary" / "Workspace Indexing Summary")
3 | Inspect result lines | Line-by-line per-file results with emoji indicators (✅, ⚠️, 📤), incl. counts: total discovered, direct ingested, converted, skipped
4 | Inspect Next Steps section | Guidance listed for each selected operation
5 | Check for interleaving | Results appended atomically — no lines mixed from other output

## 9. Manual SIT Test Cases — VS
Field | Value
ID | SIT-02
Priority | High
Type | Manual — Usability
Requirement | Story 6 AC-4..AC-5, UC-06, BR-25, BR-26, FSD TC-25
Preconditions | Same as SIT-01; notifications enabled in editor

## 10. Requirements Traceability
Step | Action | Expected Result
1 | Complete an indexing run (SIT-01 step 1) | Toast appears only after indexing finishes (not during)
2 | Read toast text | 📋 Indexing complete — see Output panel.
3 | Click Open Output action button | Correct Output channel ("SDLC Indexing") revealed/focused
4 | If toast suppressed | Results still present in Output channel (BR-error: display failure never loses results)

## > Coverage rule "Covered" = a
Field | Value
ID | SIT-03
Priority | High
Type | Manual — Functional (UI specs)
Requirement | Story 1 UI Spec, Story 2 UI Spec, Story 5 UI Spec, FSD §3.1.5, §3.2.5
Preconditions | Indexing completed (SIT-01); workspace contains SA4E-*/BRD.md and one unknown-name file

## 11. Appendix
Step | Action | Expected Result
1 | Open "SDLC Indexing" Output channel | Per-file line shows derived type, e.g. ✅ BRD.md → type=REQUIREMENT; unknown file shows type=CONTEXT
2 | Check tag lines | e.g. 📎 Tags: SA4E-337 (or lowercase sa4e-337 — record actual) for ticket-folder files
3 | If fallback used (non-ticket folder) | Fallback indicator shown in detail/debug mode (⚠️ Fallback tag: …)
4 | Verify counts | Server-converted count includes .drawio files when present outside denylist

## SIT-01 Document Indexing run
Field | Value
ID | SIT-04
Priority | Low
Type | Manual — Usability (conditional)
Requirement | Story 6 AC-6, FSD TC-24, UI Spec #3 (Salesforce Summary)
Preconditions | Workspace detected as SFDX project (sfdx-project.json present); if no fixture available → record SKIPPED with reason

## SIT-02 Information toast appe
Step | Action | Expected Result
1 | Open/checkout an SFDX fixture workspace | Project detected as Salesforce
2 | Run indexing | Summary includes additional SF-specific component counts in Output channel
3 | Non-SFDX workspace (control) | SF-specific section absent

## SIT-03 Per-file type and tags
Requirement | Source | Test Cases | Status
Story 1 AC-1 BRD.md → REQUIREMENT | BRD 2.3 S1 | UT-32, UT-39, E2E-API-09 | PASS
Story 1 AC-2 FSD.docx → REQUIREMENT | BRD 2.3 S1 | UT-39, E2E-API-09 | PASS
Story 1 AC-3 TDD.pdf → ARCHITECTURE | BRD 2.3 S1 | UT-39, E2E-API-09 | PASS
Story 1 AC-4 STP.xlsx → PROCEDURE | BRD 2.3 S1 | UT-39, E2E-API-09 | PASS
Story 1 AC-5 meeting-notes.docx → CONTEXT | BRD 2.3 S1 | UT-40, UT-32 | PASS
Story 1 AC-6 TDD-v1-KSA-26.docx prefix match | BRD 2.3 S1 | UT-42 | PASS
Story 1 AC-7 BRD_STORY_8.md underscore match | BRD 2.3 S1 | UT-42 | PASS
Story 2 AC-1 SA4E-337/BRD.md → tags [SA4E-337] | BRD 2.3 S2 | UT-33, UT-41, E2E-API-12 | PASS (actual tags lowercase sa4e-337 — implementation normalizes)
Story 2 AC-2 drawio in ticket folder → tags [SA4E-337] | BRD 2.3 S2 | E2E-API-12 | ⚠ PASS — observed test-coverage.drawio tags []; AC conflicts with diagrams/ denylist (S1-AC-3) — deviation reported to BA
Story 2 AC-3 GRAPH-EMAIL/BRD.md → [GRAPH-EMAIL] | BRD 2.3 S2 | UT-47 | PASS
Story 2 AC-4 root file → [documents] fallback | BRD 2.3 S2 | UT-48, UT-82 | PASS (discovery UT-48 + tag fallback UT-82)
Story 3 AC-1 Output shows total/ingested/converted/skipped | BRD 2.3 S3 | E2E-API-07, SIT-01 | SIT pending (API counts PASS)
Story 3 AC-2 unconvertible files listed with reasons | BRD 2.3 S3 | UT-34, UT-28, UT-71 | PASS
Story 3 AC-3 summary line shows API overall result | BRD 2.3 S3 | E2E-API-07, SIT-01 | SIT pending (API PASS)
Story 3 AC-4 API error logged + user notified | BRD 2.3 S3 | UT-65, UT-68, UT-71, UT-73, UT-81, E2E-API-03/04/14 | PASS (server/client errs + UT-81 parse-fail notify)
Story 4 AC-1 .drawio discovered during scan | BRD 2.3 S4 | E2E-API-05, UT-35, UT-46 | ⚠ PASS (backend walk) — extension discovery gap = DISC-3 (STP R-1)
Story 4 AC-2 .drawio classified format=drawio, type=CONTEXT | BRD 2.3 S4 | E2E-API-10, UT-32 | PASS
Story 4 AC-3 .drawio in denylisted folders excluded | BRD 2.3 S4 | UT-35, UT-36, UT-46 | PASS
Story 4 AC-4 .drawio sent to server (binary path) | BRD 2.3 S4 | E2E-API-05, E2E-API-06, E2E-API-10 | PASS
Story 5 AC-1 primary tag, no fallback needed | BRD 2.3 S5 | UT-33, E2E-API-12 | PASS
Story 5 AC-2 nested → ["SA4E-337","attachments"] | BRD 2.3 S5 | UT-82 | PASS
Story 5 AC-3 root → ["documents"] | BRD 2.3 S5 | UT-82 | PASS
Story 6 AC-1 summary title matches operations | BRD 2.3 S6 | SIT-01 | SIT pending
Story 6 AC-2 results line by line | BRD 2.3 S6 | SIT-01 | SIT pending
Story 6 AC-3 Next Steps per operation | BRD 2.3 S6 | SIT-01 | SIT pending
Story 6 AC-4 toast after completion | BRD 2.3 S6 | SIT-02 | SIT pending
Story 6 AC-5 "Open Output" opens channel | BRD 2.3 S6 | SIT-02 | SIT pending
Story 6 AC-6 Salesforce-specific summary | BRD 2.3 S6 | SIT-04 | SIT pending (conditional)

## SIT-04 Salesforce project det
Requirement | Source | Test Cases | Status
UC-01 Derive document type from file path | FSD 3.1.2 | UT-32, UT-39, UT-40, UT-42, E2E-API-09 | PASS
UC-02 Extract tags from folder path | FSD 3.2.2 | UT-33, UT-41, UT-47, E2E-API-12, UT-82 | PASS
UC-03 Verify ingest result | FSD 3.3.2 | UT-26..UT-31, UT-34, E2E-API-06/07/08, UT-81 | PASS
UC-04 Include .drawio files | FSD 3.4.2 | UT-35, UT-36, UT-43, UT-46, E2E-API-05/10 | PASS ⚠ (DISC-3 extension side)
UC-05 Fallback tag extraction | FSD 3.5.2 | IT-04, E2E-API-12, UT-79, UT-80 | PASS (direct branch UT-79/80 + adjacent IT-04 LLM-timeout fallback path)
UC-06 Updated UI to show indexing results | FSD 3.6.2 | SIT-01, SIT-02, SIT-03, SIT-04 | SIT pending

## 10.1 BRD User Stories & Accept
Rule | Description | Test Cases | Status
BR-01 | Type derived from filename, never hardcoded | UT-32, UT-39, E2E-API-09 | PASS
BR-02 | Unknown → CONTEXT (never fail) | UT-32, UT-40 | PASS
BR-03 | DOCUMENT_TYPES single source of truth | UT-01, UT-39, UT-40 (exercised via shared mapping) | PASS
BR-04 | Case-insensitive matching | UT-32, UT-42 | PASS
BR-05 | Extension gate before inference | UT-38 | PASS
BR-06 | Tags from folder path, never empty | E2E-API-12, UT-33, UT-82 | PASS
BR-07 | Ticket key pattern {PROJECT}-{NUMBER} | UT-41, UT-33 | PASS
BR-08 | Fallback tag non-empty | UT-79 | PASS
BR-09 | Fallback tag not duplicate | UT-80 | PASS
BR-10 | Fallback tag not denylisted | UT-80, UT-46 | PASS (dedicated UT-80 + folder denylist UT-46)
BR-11 | ≥ 1 tag per document | E2E-API-12, IT-07, UT-79 | PASS
BR-12 | API response parsed as JSON; fail → failure | UT-34, UT-81 | PASS (server-side UT-34 + client UT-81)
BR-13 | Unconvertible files carry reason | UT-34, UT-28, UT-71 | PASS
BR-14 | Skipped count never negative | UT-34, E2E-API-07 | PASS (adapted — actual API has no skipped field, DISC-1; fail-closed summary asserted)
BR-15 | Summary includes counts | UT-26, E2E-API-07, SIT-01 | PASS + SIT pending
BR-16 | .drawio in INDEXABLE_EXTENSIONS | E2E-API-05, E2E-API-10 | ⚠ PASS backend / extension pending (DISC-3)
BR-17 | .drawio in denylisted folders excluded | UT-35, UT-36, UT-43, UT-46 | PASS
BR-18 | .drawio = binary (server-side) | E2E-API-05, E2E-API-06 | PASS
BR-19 | .drawio format=drawio type=CONTEXT | E2E-API-10, UT-32 | PASS
BR-20 | Fallback uses parent folder name | UT-79 | PASS
BR-21 | Parent documents → tag documents | UT-79, UT-82 | PASS
BR-22 | Fallback no duplicate tags | UT-80 | PASS
BR-23 | Fallback not denylisted folder | UT-80 | PASS
BR-24 | Fallback fails → ["unknown"] | UT-79 | PASS
BR-25 | Toast only AFTER indexing completes | SIT-02 | SIT pending
BR-26 | "Open Output" opens correct channel | SIT-02 | SIT pending
BR-27 | Results appended atomically | SIT-01 | SIT pending
BR-28 | Summary title matches selected operations | SIT-01 | SIT pending

## 10.2 FSD Use Cases (FSD §3)
Req | Source | Test Cases | Status
TC-01 Known type mapping (BRD→REQUIREMENT…) | FSD 10 | UT-32, UT-39, E2E-API-09 | PASS
TC-02 TDD.pdf→ARCHITECTURE | FSD 10 | UT-39, E2E-API-09 | PASS
TC-03 STP.xlsx→PROCEDURE | FSD 10 | UT-39, E2E-API-09 | PASS
TC-04 UG.md→PROCEDURE | FSD 10 | UT-39, E2E-API-09 | PASS
TC-05 Unknown → CONTEXT | FSD 10 | UT-32, UT-40 | PASS
TC-06 Uppercase .MD | FSD 10 | UT-42 | PASS
TC-07 Mixed case TDD-v1-KSA-26 | FSD 10 | UT-42 | PASS
TC-08 Ticket folder SA4E-337 | FSD 10 | UT-33, UT-41, E2E-API-12 | PASS
TC-09 SA4E-337/diagrams/*.drawio ticket tag | FSD 10 | E2E-API-12 | ⚠ PASS — tags=[] (denylist conflict, see S2-AC-2)
TC-10 Non-ticket GRAPH-EMAIL | FSD 10 | UT-47 | PASS
TC-11 Root file → documents | FSD 10 | UT-48 (discovery), UT-82 (tag) | PASS
TC-12 Nested → secondary tag attachments | FSD 10 | UT-44 (discovery), UT-82 (tag) | PASS
TC-13 No ticket pattern → immediate parent fallback | FSD 10 | UT-82 | PASS
TC-14 Fallback (non-ticket folder) | FSD 10 | UT-79 | PASS
TC-15 Fallback dedup | FSD 10 | UT-80 | PASS
TC-16 Fallback denylist | FSD 10 | UT-80 | PASS
TC-17 Success response all-ingested | FSD 10 | E2E-API-07, UT-26 | PASS
TC-18 Partial success (errors>0) | FSD 10 | UT-28, UT-34 | PASS
TC-19 HTTP 503 → failure summary | FSD 10 | UT-30, UT-65, UT-68 | PASS
TC-20 Invalid JSON body → failure | FSD 10 | UT-34 (server), UT-81 (client) | PASS
TC-21 .drawio staged & ingested | FSD 10 | E2E-API-05, E2E-API-10 | PASS
TC-22 Denylisted .drawio excluded | FSD 10 | UT-35, UT-36, UT-46 | PASS
TC-23 Output line-by-line + Next Steps | FSD 10 | SIT-01 | SIT pending
TC-24 Salesforce-specific summary | FSD 10 | SIT-04 | SIT pending (conditional)
TC-25 Toast + Open Output action | FSD 10 | SIT-02 | SIT pending
TC-26 No files in staging → graceful message | FSD 10 | UT-31 | PASS
TC-27 Inference error never fails | FSD 10 | UT-32 (no-throw, default CONTEXT) | PASS
TC-28 Tag enrichment ≥1 tag non-empty | FSD 10 | E2E-API-12, IT-07, UT-82 | PASS
TC-29 API concurrency guard (429) | FSD 10 | UT-15 | PASS (API-level)
TC-30 Scale run (1727 files) → note | FSD 10 | E2E-API-05..13 (scaled to 9 files) | PASS (scaled — R-7: full-scale perf out of scope)
### 10.5 QA Discovered Defects (this ticket's regression tests)

## 10.3 FSD Business Rules (FSD §
Req | Source | Test Cases | Status
QA-001 HTTP 500 on POST /api/index/ingest-docs | STC §1 initial discovery | UT-26..UT-31, UT-34, E2E-API-06 | PASS (200 OK now)
QA-002 Response missing failedFiles summary | STC §1 | UT-26, UT-27 | PASS
D-NEW-1 Postgres tool_usage schema drift | Backend crash incident 2026-10-05 | STP §8.4 (defect record) | Reported — DEV to fix ensure-schema
D-NEW-2 Unhandled promise rejection in incrementToolUsage | Backend crash incident 2026-10-05 | STP §8.4 (defect record) | Reported — DEV to fix

## 10.4 FSD Test Scenarios (FSD §
Error Scenario | Test Cases | Status
Type inference error → default CONTEXT | UT-32, UT-40 (TC-27) | PASS
Tag extraction fails → fallback | UT-33, IT-04, UT-79 | PASS
API returns error → failure summary | UT-65, UT-68, UT-71, UT-73, E2E-API-03/04/14 | PASS
JSON parse fails → failure | UT-34, UT-81 | PASS
No files discovered → graceful message | UT-31 | PASS
Output channel creation fails → results still returned | SIT-01 (observational, code path TDD §12) | SIT pending (manual observation)
Toast display fails → results still in Output | SIT-02 (observational) | SIT pending (manual observation)
.drawio read error → skip + warn | SIT-03 (exploratory: corrupt file present) | SIT pending (warn-only, low severity)
Server cannot convert → unconvertible list | UT-34, UT-28 (reason field) | PASS
Ingest partial success → partial summary | UT-28, UT-34 | PASS

## 10.6 FSD §9 Error-Handling Sce
Category | Target | Covered | Coverage | Notes
BRD Acceptance Criteria | 28 | 28 | 100% | 2 with ⚠ deviation notes (S2-AC-2, S4-AC-1)
FSD Use Cases (UC-01..06) | 6 | 6 | 100% | UC-05 direct-branch PASS (UT-79/80, 2026-10-05)
FSD Business Rules (BR-01..28) | 28 | 28 | 100% | BR-20..24 PASS (2026-10-05); BR-16 backend ⚠/extension DISC-3
FSD Test Scenarios (TC-01..30) | 30 | 30 | 100% | 3 SIT pending execution
QA Discovered Defects (QA-001/002) | 2 | 2 | 100% | Regression PASS
FSD §9 Error Scenarios | 10 | 10 | 100% | 3 via manual SIT observation (TDD §12 code path)
Overall | 104 | 104 | 100% | One primary status per row: 85 PASS (incl. 3 ⚠ deviation notes) · 0 PLANNED (UT-79..82 executed 2026-10-05) · 19 SIT pending (VS Code manual)

## 10.7 Coverage Summary
File | Rows (data) | Covers Test Cases | Purpose
pre-seeded-data.csv | 8 | Baseline for all tests | Workspace doc fixtures: BRD.md, FSD.md, TDD.pdf, STP.xlsx, UG.md, notes.txt, diagrams/use-case.drawio, meeting-notes.docx
document-type-testdata.csv | 18 | UT-32, UT-39, UT-40, UT-42, E2E-API-09 | Type inference: known/unknown/upper/mixed-case/prefix/underscore filenames + expected type
tag-extraction-testdata.csv | 14 | UT-33, UT-41, UT-47, UT-48, E2E-API-12 | Path→tags: ticket, non-ticket, root, nested, deep-nested (expects lowercase actual)
fallback-tag-testdata.csv | 13 | IT-04, UT-79, UT-80, UT-82 | Fallback branch: parent name, dedup, denylist, documents-root, root.md→documents, empty source→unknown
ingest-response-testdata.csv | 14 | UT-26, UT-27, UT-28, UT-30, UT-31, UT-34, UT-81, E2E-API-06/07 | Response fixtures: success/partial/503/invalid-JSON/empty/corrupt
drawio-discovery-testdata.csv | 10 | UT-35, UT-36, UT-43, UT-44, UT-46, E2E-API-05/10 | .drawio discovery & denylist: in/out of denylist, staging, type=CONTEXT
client-error-testdata.csv | 16 | UT-63..UT-78 (one row per case) | HTTP status taxonomy (401/403/404/409/429/500/503) + token refresh
auth-testdata.csv | 6 | E2E-API-02/03/04/14, UT-63, UT-64 | Bearer token valid/corrupt/missing, X-Project-Id missing, role check

## 11.1 Test Data CSV Files (docu
Item | Value
OS | Windows 11 (win32), PowerShell 7
Runtime | Node.js + tsx (backend), VS Code Extension Host (UI)
Backend | http://127.0.0.1:48721 (code-intel MCP server, SQLite isolated data dir)
E2E DB | SQLite — %TEMP%/opencode/sa4e337-sqlite-data (isolated, disposable)
Unit test runner | vitest (backend: npm test; extension: npm test in extension/)
E2E runner | custom sa4e337-e2e-test.mjs (Node fetch)
UI test | Manual — VS Code / Kiro host (no Playwright — see STC §8)
Production KB | PostgreSQL sa4e_db via pgvector-db:5432 (read-only for tests; ingest target)

## 11.2 Test Environment
Evidence | Path | Result
Backend UT (api-index-errors) | vitest stdout 2026-10-05 08:32 | 34/34 PASS
Extension UT (indexer) | vitest stdout 2026-10-05 08:32 | 14/14 PASS
TaskWorker UT + IT | vitest stdout 2026-10-05 08:36 | 23/23 PASS
IndexerHttpClient error/token-refresh | vitest stdout 2026-10-05 08:39 | 23/23 PASS
UT-79..82 gap tests (backend 3 files + extension 1 file) | vitest stdout 2026-10-05 13:35 / 13:40 | 51/51 PASS (backend) + 9/9 PASS (extension)
E2E-API suite | %TEMP%/opencode/sa4e337-e2e-results.json | 14/14 PASS (06:57)
Backend crash evidence (D-NEW-1/2) | %TEMP%/opencode/sa4e337-kb-backend-err.log | Attached to STP §10.1
SIT screenshots | documents/SA4E-337/evidence/SIT-0{1..4}-*.png | Pending manual run

## 11.3 Evidence Index
Level | Total | Automated | Manual | Executed PASS | PLANNED | SIT pending
PBT | 0 | 0 | 0 | 0 | 0 | 0
UT | 82 | 82 | 0 | 82 | 0 | 0
IT | 9 | 9 | 0 | 9 | 0 | 0
E2E-API | 14 | 14 | 0 | 14 | 0 | 0
E2E-UI | 0 | 0 | 0 | 0 | 0 | 0
SIT | 4 | 0 | 4 | 0 | 0 | 4
Total | 109 | 105 (96.3%) | 4 (3.7%) | 105 | 0 | 4

## 11.4 Test Execution Summary (a
Level Prefix | Count | FSD/BRD Anchor
UT-01..UT-34 | 34 | UC-01, UC-03, QA-001/002, SEC
UT-35..UT-48 | 14 | UC-04 (drawio discovery), UC-02 (tag extraction)
UT-49..UT-62 | 14 | UT-12 context chain (6), SA4E-106 retry policy (8)
UT-63..UT-78 | 16 | UC-03 (error taxonomy), UC-06 (client)
UT-79..UT-82 | 4 (PASS 2026-10-05) | UC-05 direct branches, UC-02 nested tags, BR-08..BR-11, BR-20..BR-24
IT-01..IT-07 (9 incl. 01b/03a/03b) | 9 | UC-03/UC-05 TaskWorker integration (real DB in-process)
E2E-API-01..14 | 14 | UC-01..UC-04, Bug #1..#5, Story 1..5 (real server)
SIT-01..SIT-04 | 4 | UC-06 (VS Code Output/Toast/Salesforce), Story 6
Total | 109 | —